## Slide 1: Harvard Assets Project

## Slide 2: Agenda
Project Update
Roles & Responsibilities
Equipster Data Conversion Update

## Slide 3: Project Update – High Level Project Timeline
Project Phases | 2013 |  |  |  |  |  |  |  |  |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  | 
 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Discovery Phase (6/1/2012-4/30/2013) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Planning & Analysis Phase (12/15/2012-6/30/2013) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Build Phase (6/1/2013 – 12/15/2013) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Test Phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Phase 1 - 3 Rollout |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Closure Phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
100%
100%
Indicates percentage of work complete.
Indicates percentage of unfinished work.
Future phases.
High-level planning; set-up of project structure
Business requirements & process design, detailed project and change management planning, including project roll-out timing and participants
Configuration and development, interactive prototype demo sessions (IPDs), detailed business process flows
Full system testing and sign-off
Training, data conversion (including development & testing), post-production support
Lessons learned, archiving project artifacts
Key deliverables / activities by phase
100%
98%
20%

## Slide 4: Roll-Out Strategy – Oracle Assets and AP Adjustments
Project Phases | Calendar Year 2014 |  |  |  |  |  |  |  |  |  |  | 
 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Roll-Out 1 (4/1 – Go Live) |  |  |  |  |  |  |  |  |  |  |  | 
AP Adjustments for Assets (4/1 – Go Live) |  |  |  |  |  |  |  |  |  |  |  | 
Roll-Out 2 (7/1 – Go Live) |  |  |  |  |  |  |  |  |  |  |  | 
Roll-Out 3 (10/1 – Go Live) |  |  |  |  |  |  |  |  |  |  |  | 
GSE, HKS, GSD, HLS, HBS, Radcliffe, Divinity, SPH, FAS Athletics and DCE
FAS, HMS, SEAS, HSDM
Campus Service, HUIT, CAD, Allied & Affiliates, UHS
UNIVERSITY WIDE

## Slide 5: FAS Responsibility Implications

## Slide 6: Future State Roles & Responsibilities - Descriptions

## Slide 7: Equipster Data Conversion Update
Technical mapping of data to Oracle Assets underway
Data to GL reconciliation being lead by Finance
Need for accurate / up-to-date Equipster data:
  Assign all transactions
  Close all necessary WIP / Fabrications
  Update Equipster records as necessary